## Sheet1
Work Breakdown Structure
WBS ID | Task Name | Task Description | Owner | Milestone/Deliverable | Estimated Duration
1.0 | HealthFirst Care Improvement Initiative | Overall project structure and execution | Project Manager | Full Project Plan | 6 months
1.1 | Requirements Gathering | Gather and analyze all requirements | Business Analyst | Requirements Document | 2 weeks
1.1.1 | Conduct Interviews | Meet with stakeholders to understand needs | Business Analyst | Interview Notes | 3 days
1.1.2 | Analyze Data | Review appointment and feedback data | Data Analyst | Data Analysis Summary | 3 days
1.1.3 | Finalize BRD & RTM | Finalize documentation for BRD and RTM | BA Lead | Signed BRD/RTM | 4 days
1.2 | System Design | Design the architecture for implementation | System Architect | System Architecture | 3 weeks
1.2.1 | Define Requirements | Specify detailed technical requirements | IT Lead | Requirement Specs | 5 days
1.2.2 | Create Wireframes | Design wireframes for new scheduling system | UI Designer | Wireframes | 4 days
1.2.3 | Plan Architecture | Create system architecture and integration plan | System Architect | Integration Plan | 6 days
1.3 | Development | Develop and implement core systems | Dev Team | System Modules | 6 weeks
1.3.1 | Build Scheduling System | Develop and code the scheduling module | Dev Team | Scheduling Module | 10 days
1.3.2 | Develop Notifications | Create SMS/email notification system | Dev Team | Notification System | 7 days
1.3.3 | Dashboard Development | Develop real-time dashboard interface | Dev Team | Resource Dashboard | 8 days
1.3.4 | Centralize EHR | Implement central patient record system | Dev Team | Central EHR | 9 days
1.4 | Testing & Validation | Test functionality and validate scope | QA Team | Testing Complete | 2 weeks
1.4.1 | System Testing | Execute system-wide testing | QA Team | Test Report | 5 days
1.4.2 | User Acceptance Testing | Get user validation and sign-off | Stakeholders | UAT Approval | 3 days
1.4.3 | Validate Requirements | Ensure alignment with BRD/RTM | BA & QA Team | Validation Summary | 2 days
1.5 | Training & Rollout | Train and roll out to all staff | Training Lead | Staff Rollout | 2 weeks
1.5.1 | Create Training Materials | Write user guides and training content | Documentation Team | Training Docs | 3 days
1.5.2 | Train Staff | Conduct formal training for all users | Training Lead | Training Logs | 4 days
1.5.3 | Go-Live | Deploy system live for use | IT Team | Live Deployment | 3 days
1.6 | Monitoring & Feedback | Monitor and sustain the project post-launch | Support Team | Sustainment Plan | 4 weeks
1.6.1 | Monitor Usage | Track system performance and uptime | IT Team | Performance Report | 5 days
1.6.2 | Collect Feedback | Capture user and system feedback | Business Analyst | Feedback Report | 3 days
1.6.3 | Continuous Improvement | Enhance based on continuous feedback | IT/Dev Team | Improvement Plan | 12 days
Milestones
Completion of stakeholder interviews
Finalization of BRD
System development complete
Stakeholder sign-off on final implementation
Project closure and retrospective