## Risk Register
Risk ID | Risk description | Risk Category | Likelihood | Impact | Severity | Mitigation Strategy
R001 | Manual scheduling process causes delays and errors | Operational | High | High | Critical Risk | Implement automated scheduling system
R002 | Staff resistance to new digital tools | Stakeholder | Medium | High | High-priority Issue | Conduct training and change management sessions
R003 | Patient data breach due to poor cybersecurity | Technical | Medium | High | High-priority Issue | Conduct regular data audits and improve encryption
R004 | System downtime during peak hours | Technical | Medium | Medium | Mitigation Required | Establish redundancy and support for downtime recovery
R005 | Inconsistent resource utilization across departments | Operational | High | Medium | Mitigation Required | Use a centralized resource tracking dashboard
R006 | Budget overruns due to underestimation of system costs | Financial | Low | Medium | Monitor Closely | Conduct detailed financial planning and maintain contingency reserve
R007 | Delays in project approval due to non-compliance with healthcare regulations | Regulatory & Compliance | Low | High | Address if escalated | Engage compliance officers early and conduct regular regulatory reviews
R008 | Delay in lab report delivery during peak testing hours | Operational | Low | Low | Minor Concern | Automate sample tracking and optimize lab workflow scheduling

## Risk Assessment MatrixL
Likelihood | Low Impact | Medium Impact | High Impact
Low | R008 | R006 | R007
Medium |  | R004 | R002, R003
High |  | R005 | R001