## Sheet1
Risk ID | Contingency Plan
R001 | Shift to manual paper-based scheduling temporarily, increase admin staff coverage during high-volume periods, and notify patients of delays.
R002 | If resistance continues, introduce change champions within departments, extend training duration, and provide one-on-one support sessions
R003 | Immediately isolate affected systems, notify IT security team, conduct root cause analysis, and communicate breach resolution to stakeholders
R004 | Switch to backup systems, notify stakeholders of delay, and activate emergency IT support to restore operations.
R005 | Temporarily reassign staff and equipment from low-load to high-load departments and alert department heads to adjust workflows
R006 | Reallocate resources from non-critical areas, escalate to project finance team, and delay optional features if required to control budget